## Sheet1
ID | As a.. | I want to be able to… | So that… | Priority | Sprint | Status | Functionality Implemented | Tested?
1 | Student | access this application from a browser | it doesn't take up valuable space on my devices | Must | 3 | Complete | Web Application - Database link
2 | Student | login before viewing my infomration | it is only accessible by me | Must | 3 | Complete | Login In and Log out
3 | Student | add courses and their details | be more organised visually | Must | 4 | Complete | Add Course
4 | Student | add assignments and their details | be more organised visually | Must | 4 | In progress | Add Assignment
5 | Student | add exams and their details | be more organised visually | Must | 4 | In progress | Add Exam
6 | Student | view previously added courses, assignments and exams when I login in another time | I don't have repeatedly add them | Must | 4 | Complete | Course, Exam, Assignment pages, Database persistence
7 | Student | delete previously added courses, assignment, exams | They don't remain on the website inndefinitely | Must | 4 | Complete | Delete Course, Assignment, Exam
8 | Student | easily visualize my exams and assignment deadlines | I don't miss any of them | Must | 4 | In progress | Dashboard
9 | Student | modify details on courses, assignments and exams added | they can reflect real life changes, and I can correct errors. | Must | 5 | To be started | Modify Courses, Assignments, Exams
10 | Student | mark my assignments as completed | my to do list reduces when I have completed a task | Must | 5 | To be started | Change assignement state to completed
11 | Student | be reminded of upcoming deadlines | I don't forget them | Should | 5 | To be started | Alerts
12 | Student | see a colour coded list of assignments | I can easily identify which ones are due soon | Could | 5 | To be started | Coloured lists
13 | Student | login in with my Google account | I have guranteed password security | Could |  | Future sprint | Google Sign In API
14 | Student | view my upcoming activities on a calander | I have an idea of the time between each due date | Could |  | Future sprint | Calendar page
15 | Student | share my schedule with friends | we can schedule activities together | Could |  | Future sprint | Google Calendar API?